PERFECT SKILLS FRAS Pilot — Scope of Work Face Recognition Attendance System ¦ 1-Classroom Pilot March 2026 ¦ Confidential

SECTION 1

Pilot Overview

This document defines the scope, responsibilities, deliverables, and timeline for a 1-classroom pilot deployment of the Face Recognition Attendance System (FRAS) at [Institution Name].

The objective of the pilot is to demonstrate the full end-to-end FRAS pipeline — from camera capture to live attendance logging — in a real classroom environment, before committing to a full 150-classroom rollout.

| Field | Detail |
| --- | --- |
| Client | Institution |
| Vendor | Perfect Skills |
| Pilot Scale | 1 Classroom ¦ 1 Camera ¦ 1 Section |
| Pilot Type | Live Environment — real students, real attendance |
| Duration | 5-7 Working Days from the date hardware is ready |
| Deployment Mode | Virtual + On-Premise — all processing on the institution's local machine |

SECTION 2

What Is Included in This Pilot

The pilot covers the complete FRAS workflow for one classroom:

| 01 | Software Installation: Full FRAS software stack installed and configured on the institution's provided machine. |
| --- | --- |
| 02 | RTSP Camera Setup: RTSP stream ingestion configured and tested for the pilot classroom camera. |
| 03 | Student Enrollment: Photos processed, ArcFace embeddings generated, and local vector DB built for the pilot class. |
| 04 | Live Attendance Sessions: Minimum 3 live attendance capture sessions run during the pilot period. |
| 05 | Accuracy Report: Post-pilot report showing identification accuracy, confidence scores, and detection statistics. |
| 06 | Dashboard Access: Web-based attendance dashboard deployed on the institution's local network for the pilot class. |
| 07 | Calibration & Tuning: Threshold and camera setting adjustments based on pilot session results. |
| 08 | Handover Notes: Observations, recommendations for full deployment, and next steps document. |

SECTION 3

What Is Not Included in This Pilot

The following are explicitly outside the scope of the pilot and remain the institution's responsibility:

The following items are out of scope for this pilot:

- Procurement or installation of the camera or mounting hardware

- Server procurement, setup, or OS installation

- Network cabling or Gigabit LAN setup between the camera and server

- Collection of student photos and preparation of the metadata CSV

- Classroom timetable data or ERP integration (out of scope for pilot)

- Deployment of the system in any classroom other than the designated pilot room

SECTION 4

Responsibilities

Perfect Skills (Vendor)

- Install and configure the FRAS software stack on the provided machine

- Set up and test RTSP ingestion from the pilot classroom camera

- Run the student enrollment pipeline — process photos, generate embeddings, build vector DB

- Deploy the web-based attendance dashboard on the institution's local network

- Conduct minimum 3 live attendance capture sessions and calibrate thresholds

- Deliver an accuracy and performance report at the end of the pilot

- Provide handover notes and full-deployment recommendations

Institution (Client)

- Provide a server or dedicated machine meeting the minimum specifications (see Checklist)

- Provide 1 RTSP-compatible IP camera, mounted correctly in the pilot classroom

- Ensure Gigabit LAN connectivity between the camera and the server

- Collect and submit 3–4 photos per student for the pilot class, plus metadata CSV

- Provide classroom access during the pilot sessions

- Designate a technical contact point for coordination during the pilot

SECTION 5

Pilot Timeline — 5 Working Days

The following timeline begins from the date all hardware and student data is ready and access is provided.

| Day | Focus | Activities |
| --- | --- | --- |
| Day 1 | Setup | Server access, software installation, RTSP camera connectivity test, dependency verification. |
| Day 2 | Enrollment | Process student photos, generate ArcFace embeddings, build FAISS vector DB for pilot class. |
| Day 3 | Integration | Integrate the platform with local infrastructure |
| Day 4 | Live Session 1 | First live attendance capture. Validate detections, review confidence scores, initial calibration. |
| Day 5 | Live Session 2 & 3 | Two more live sessions. Tune thresholds, handle edge cases (glasses, lighting variance). |
| Day 6 | Report & Handover | Generate accuracy report, dashboard demo, deliver findings and full-deployment recommendations. |

SECTION 6

Pilot Success Criteria

The pilot will be considered successful if the following criteria are met:

✓ Identification Accuracy ≥ 85% At least 85% of students in the pilot class correctly identified across live sessions. (90–95% expected with optimal camera placement.)

✓ False Positives < 2% Fewer than 2% of attendance records flagged as Present for students who were absent.

✓ Live Dashboard Operational Attendance records visible on the web dashboard within 5 minutes of each session.

✓ 3 Successful Live Sessions Minimum 3 live capture sessions completed without system failure.

AUTHORISATION

Agreement & Sign-Off

Both parties agree to the scope, responsibilities, and commercial terms outlined in this document.

| For Perfect Skills Signature Name: _______________________ Date: _______________________ | For [Institution Name] Signature Name: _______________________ Date: _______________________ |
| --- | --- |

This document is confidential and prepared exclusively for the named institution.